## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project | MUST HAVE | No Dependency | Suryakala R | 3- Completed
S1 | S1 | US-001 | Define Knowledge Graph Schema (Entities & Relations) | MUST HAVE | No Dependency | Suryakala R | 3- Completed
S2 | S2 | US-001 | Build Data Ingestion Pipeline (Documents, CSV) | MUST HAVE | Python Libraries | Suryakala R | 3- Completed
S2 | S2 | US-001 | Data Cleaning & Normalization Module | MUST HAVE | Pandas | Suryakala R | 3- Completed
S2 | S2 | US-001 | Index Processed Data for Further Extraction | SHOULD HAVE | File Processing Logic | Suryakala R | 3- Completed
S3 | S3 | US-001 | Implement LLM-based Named Entity Recognition (NER) | MUST HAVE | OpenAI / LLM API | Suryakala R | 3- Completed
S3 | S3 | US-001 | Relationship Extraction Between Entities | MUST HAVE | NER Output | Suryakala R | 3- Completed
S4 | S4 | US-001 | Store Extracted Triples in Neo4j | MUST HAVE | Neo4j Driver | Suryakala R | 3- Completed
S4 | S4 | US-001 | Enable Incremental Graph Updates | SHOULD HAVE | Existing Graph | Suryakala R | 3- Completed
S5 | S5 | US-001 | Generate Embeddings using LangChain | MUST HAVE | LangChain | Suryakala R | 3- Completed
S5 | S5 | US-001 | Integrate Vector Database (FAISS/Pinecone) | MUST HAVE | Embeddings | Suryakala R | 3- Completed
S6 | S6 | US-001 | Implement RAG-based Semantic Search | MUST HAVE | Vector DB | Suryakala R | 3- Completed
S7 | S7 | US-001 | Develop Graph Visualization UI | MUST HAVE | Graph API | Suryakala R | 3- Completed
S7 | S7 | US-001 | Implement Search & Filtering in Dashboard | COULD HAVE | UI Framework | Suryakala R | 3- Completed
S8 | S8 | US-001 | Drill-down Entity Insight View | MUST HAVE | Dashboard | Suryakala R | 3- Completed
S8 | S8 | US-001 | End-to-End System Testing | SHOULD HAVE | All Modules | Suryakala R | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 97 | 26 | 28 | 25 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to project | 2025-12-29 | 2025-12-30 | Suryakala R | Others | Must Have | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Workflow Creation and Project Goal Document | 2025-12-31 | 2025-12-31 | Suryakala R | Design | Should Have | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Data Collection Setup | 2026-01-05 | 2026-01-06 | Suryakala R | Coding | Must Have | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Data Cleaning & Preprocessing | 2026-01-09 | 2026-01-10 | Suryakala R | Coding | Must Have | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Entity Extraction (NER) | 2026-01-12 | 2026-01-12 | Suryakala R | Coding | Must Have | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Relationship Extraction | 2026-01-21 | 2026-01-21 | Suryakala R | Coding | Must Have | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Triple Generation | 2026-01-22 | 2026-01-22 | Suryakala R | Development | Must Have | 6 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Neo4j Integration | 2026-01-28 | 2026-01-28 | Suryakala R | Integration | Must Have | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Cypher Query Testing | 2026-02-03 | 2026-02-04 | Suryakala R | Testing | Must Have | 6 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Embedding Generation | 2026-02-06 | 2026-02-09 | Suryakala R | Development | Should Have | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 11 | Vector DB Integration | 2026-02-10 | 2026-02-12 | Suryakala R | Integration | Should Have | 7 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 12 | RAG Semantic Search | 2026-02-13 | 2026-02-16 | Suryakala R | Testing | Must Have | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 13 | Dashboard Basic UI | 2026-02-19 | 2026-02-24 | Suryakala R | Development | Should Have | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 14 | Final Testing & Documentation | 2026-02-24 | 2026-02-25 | Suryakala R | Others | Must Have | 6 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 6 | Faced confusion while designing the knowledge graph structure | Discussed with mentor and finalized the main entities and relationships.
Sprint 2 | Day 7 | Trouble connecting Python with Neo4j database. | Checked configuration and successfully established the connection.
Sprint 3 | Day 12 | Entity extraction was not giving accurate results | Improved the prompt and tested multiple samples to get better output.
Sprint 4 | Day 16 | Duplicate nodes were getting created in the graph. | Modified Cypher queries using MERGE to avoid duplication.
Sprint 5 | Day 23 | Difficulty integrating semantic search with graph queries. | Refactored the logic and connected both modules properly.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 2 | 2026-01-05 | 2026-01-10 | Suryakala R | Start cleaning data before processing. | Stop using raw data directly. | Continue testing each preprocessing step. | Improved data cleaning logic
2 | Sprint 3 | 2026-01-12 | 2026-01-21 | Suryakala R | Start validating entity extraction results. | Stop assuming model output is correct. | Continue refining prompts. | Improved NER accuracy.
3 | Sprint 4 | 2026-01-28 | 2026-02-03 | Suryakala R | Start checking graph structure before storing. | Stop using CREATE everywhere. | Continue testing Cypher queries. | Used MERGE to prevent duplicates.
4 | Sprint 5 | 2026-02-06 | 2026-02-10 | Suryakala R | Start verifying data before Neo4j insertion. | Stop creating duplicate nodes. | Continue query testing | Optimized Neo4j queries.
5 | Sprint 6 | 2026-02-13 | 2026-02-19 | Suryakala R | Start refining preprocessing for better mapping. | Stop ignoring small data issues. | Continue improving relations. | Cleaned data and improved triples.
6 | Sprint 7 | 2026-02-24 | 2026-02-25 | Suryakala R | Start testing graph and search together. | Stop integrating all modules at once. | Continue step-by-step debugging. | Improved Neo4j and RAG integration.